AGENCY CONTROL #: CSEA/SDNH/14-001-S

ATTACHMENT: Attachment P

SOLICITATION TITLE: Maryland State Directory of New Hires

| START-UP ACTIVITIES – IDENTIFY AS DAILY, WEEKLY, MONTHLY, OTHER (as necessary) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Contract Affidavit (Attachment C) | Within ten (10) work days recommendation for award | Completed & Signed Affidavit | Procurement Officer |  |
| MBE Outreach Efforts Compliance Statement (Attachment G) | Within 10 working days from notification of recommendation for award | Completed & Signed Statement | Procurement Officer |  |
| MBE Subcontractor Project Participation Certification (Attachment H) | Within 10 working days from notification of recommendation for award | Completed & Signed Certification | Procurement Officer |  |
| Certificates of Insurance | Within 10 working days from notification of recommendation for award | Current Certificate of Insurance meeting all limit requirements | Procurement Officer |  |
| Hiring Agreement (Attachment N) | Within ten (10) business days from recommended for Contract Award. | Completed & Signed Agreement | Procurement Officer |  |
| Post-Award Orientation Conference | Within five (5) business days after approval by the BPW | Sign-in sheet and meeting notes. Attendance by Contractor and/or Contractor’s Project Manager and any other Contractor staff deemed appropriate to attend | State Project Manager/ CSEA Contracts Unit/DLLR and OTHS Contact |  |

| State of Maryland Dept of Labor Licensing and Regulation Confidential Data Agreement (Exhibit 4) | Within five (5) business days of the Post Award Conference | Completed & Signed Agreement | State Project Manager/ DLLR Contact |  |
| --- | --- | --- | --- | --- |
| Submit an Annual Outreach Plan (AOP) | Within thirty (30) calendar days after the Notice to Proceed (NTP). | Receipt of AOP | State Project Manager |  |
| Provide a comprehensive project work schedule | Within three (3) calendar days from NTP | Receipt of schedule | State Project Manager |  |
| Provide a comprehensive Project Management Plan | Within seven (7) calendar days from NTP | Receipt of plan | State Project Manager |  |
| Provide a complete Communications Plan | Within seven (7) days of NTP | Receipt of plan | State Project Manager |  |
| Provide a complete Quality Management Plan | Within seven (7) days of NTP | Receipt of Plan | State Project Manager |  |
| Develop a Cost Management Plan | Within seven (7) days of NTP | Receipt of plan | State Project Manager |  |
| Deliver a final Human Resources Management Plan | Within seven (7) days of NTP | Receipt of plan | State Project Manager |  |
| Coordinate with the State Project Manager and all parties concerned to have smooth Transition-In Services | On-going | TBD | State Project Manager |  |
| Be prepared to take the database live upon receipt of a NTP from the State Project Manager. | On-Going | TBD | State Project Manager/OTHS Contact |  |
| Contact OTHS to ensure procedures are put in place to establish FTP connectivity between the Contractor and DHR’s network. | After Contract Award | Sign-in sheet if applicable, meeting notes | OTHS Contact (see Section 3.7) |  |
| Contact DLLR to establish processes and procedures for obtaining and receiving electronic files containing the names and addresses of employers that conduct business in Maryland and are covered by the UI law. | After Contract Award | Sign-in sheet if applicable, meeting notes | DLLR Contact (see Section 3.7) |  |
| Capture each data element listed on the MD Employer File Submission Layout-DHR (Attachment S) for every new hires record and the Federal Parent Locator Service National Directory Guide for Data Submission (Attachment T) to meet federal file format requirements. | Daily | Transition-In Test | State Project Manager |  |
| Review the current NHEIP packet and within five (5) business days submit for consideration to the State Project Manager an updated NHEIP that addresses any State and/or federal reporting requirements or policies enacted during the Transition-In period. | within five (5) business days | Receipt of updated NHEIP | State Project Manager |  |
| After the initial three month supply provided by the Department, maintain, replenish and mail hard copy NHEIPs to employers for the remainder of the Contract. | On-going | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Ensure that the local, national, facsimile numbers and the P.O. Box are fully operational | On day one of the Contract. | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – DAILY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Daily Scope of Work Activities Listed in Sections 3.4.2-3.4.6 | On Demand/As required by Services being provided | Monthly Reports and unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Provide MSDNH services | Monday through Friday between the hours of 8:00 A.M. through 5:00 P.M. | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Identify the Maryland State Directory of New Hires on all documentation and correspondence relating to the services performed under this Contract | On-going | MSDNH Documentation | State Project Manager |  |
| Receive new hires records from employers electronically, non-electronically, or via payroll service | On-going | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Contact employers when new hires records are incorrect, incomplete and/or rejected by the federal OCSE and request the missing or corrected data. | Within two (2) workdays | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Enter electronic and non-electronic new hires employee records into the database | Within two (2) business days after receipt of the completed record from the employer | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Notify the State Project Manager verbally when the Contractor is unable to comply with the two (2) business day requirement. The verbal notification shall be followed up in writing via email the next business day | Within 24 hours | Dated communications between Contractor’s Project Manager and the State Project Manager | State Project Manager |  |
| Ensure that the "date of receipt" and the "date of entry" for all new hires records (electronic and non-electronic) are recorded in the database. | On-going | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| In the event that employer records, employment forms, and/or other records are misdirected to CSEA or DLLR, input such records. The Contractor shall notify these employers in writing to prevent the misdirection of future submissions | within two days after receipt from CSEA or DLLR | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Create a file in the format provided in Attachment S of all new records processed on the MSDNH database. | every business day | Receipt of file | State Project Manager |  |
| forward an electronic file of newly entered records to the DHR FTP Server | every business day | Receipt of File | State Project Manager |  |
| Send to OTHS, for the purpose of forwarding to DLLR, an electronic copy of the report of new hires in the format to be agreed upon after award. | On a twice-weekly basis | Receipt of file | State Project Manager |  |
| Send to OTHS an electronic copy of the report of new hires for forwarding to the OCSE in the format provided in Attachment T. | Every business day | Receipt of report | State Project Manager |  |
| Date stamp, review, and respond to all inquiries and other correspondence relating to the MSDNH procedures. The Contractor shall retain a copy of all such inquiries and responses | On-going, as needed | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Forward requests for disclosure of information or inquires the Contractor is unable to address, including a scan of the envelope in which it was received, via encrypted email or fax to the State Project Manager | Within twenty-four (24) hours of receipt or the next business day, whichever is sooner | Receipt of requests for disclosure of information or inquiries. | State Project Manager |  |
| Input all non-electronic records received from employers into the MSDNH. The Contractor shall scan all original source documentation and save electronically. The non-electronic document shall be maintained for a minimum of 180 days; thereafter, the original source documentation may be shredded | Daily | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Maintain a back-up copy of the database including all supporting documentation and files for a period 3 years after the end of the Contract or after the complete resolution of any audit, whichever is longer | On-going | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – WEEKLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Weekly Scope of Work Activities Listed in Sections 3.4.2-3.4.6 | On Demand/As required by Services being provided |  | State Project Manager |  |
| Submit a weekly Status Report | Monday of each week | Receipt of report | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – MONTHLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Monthly Scope of Work Activities Listed in Sections 3.4.2-3.4.6 | On Demand/As required by Services being provided | Deliverables | State Project Manager |  |
| Submit monthly invoice (Attachment A-1) for services provided in the previous month. | By the 15th day of the month | Submission of completed document | State Project Manager |  |
| Receive monthly the UI employer file from DLLR. The Contractor shall compare the current UI employer file with the previous UI employer file to identify new employers and employers that are no longer reporting new hires. | TBD (see Section 3.4.2 (A)(10) and 3.4.6 (E)(4) of RFP). | TBD | DLLR Contact (TBD) |  |
| Update the MSDNH database | Within five (5) days after receipt of the UI employer file. | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Mail to each new employer a NHEIP | Within five (5) business days after receipt of the UI employer file | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Forward a list containing the names and addresses of employers from whom mail is returned undeliverable. Include steps taken by the Contractor to resolve undeliverable mail. | 15th of each month for the previous month’s activity | Receipt of List | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – ANNUALLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Daily Scope of Work Activities Listed in Sections 3.4.2-3.4.6 | On Demand/As required by Services being provided |  | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – OTHER (one time only, as requested, etc.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Other Scope of Work Activities Listed in Sections 3.4.2-3.4.6 | On Demand/As required by Services being provided |  | State Project Manager |  |
| Submit upon request a written Corrective Action Plan (CAP) that details the method of preventing and eliminating any backlog of work. The State Project Manager will review for approval, the CAP within ten (10) business days of receipt | Upon request. | Receipt of CAP | State Project Manager |  |
| Adjust staff to accommodate seasonal increases in employers’ reporting. | Typically, seasonal increases occur during the months of June and November of each year. | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Make adjustments to the database as requested by the State Project Manager or resulting from updates in federal or State requirements | Within 30 calendar days after receipt of written notice from the State Project Manager. | Receipt of database adjustment report | State Project Manager |  |
| Submit a report detailing all activity related to the required adjustments, including implementation timelines and a work plan to the State Project Manager | Within 15 calendar days before making the adjustments. | Receipt of report | State Project Manager |  |
| In the event new or revised legislative requirements are enacted by State or federal statute, review and update the current NHEIP in accordance with the new or revised legislation. The Contractor shall submit to the State Project Manager the updated version of the NHEIP for approval | Within ten (10) days after implementation of the new law | Receipt of revised NHEIP | State Project Manager |  |
| Mail the revised NHEIP to each employer on the employer file | within five (5) business days after receipt of approval from the State Project Manager | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Send a warning notice (Attachment R) to potentially non-compliant employers via first-class mail, as mandated by State and federal regulations. | Within ten (10) business days of receipt of the quarterly Federal EPP report | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| Identify employers who have an incident of non-compliance after having received a warning notice (Attachment R) | the 15th of each month following the month that the incident of non-compliance occurred | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations | State Project Manager |  |
| With respect to employers who have been deemed non-compliant, the Contractor shall: - identify employers who received a warning notice; had an opportunity to correct its reporting practice; and continued non- compliant practices. - provide a report to the State Project Manager of employers identified - Mail Penalty Assessment Notice to Non-Compliant Employers (Attachment Z) to employers identified | - Within twenty (20) business days of receipt of the quarterly Federal EPP report - Within twenty (20) business days of receipt of the quarterly Federal EPP - Within twenty (25) business days of receipt of the quarterly Federal EPP | Unannounced site-visits; random and periodic monitoring reviews and/or audits of the Contractor’s MSDNH operations; receipt of report | State Project Manager |  |

| REPORTS |  |  |  |
| --- | --- | --- | --- |
| Report Requirements / Section | Time Frame | Report Sent To | Date Received / Initials |
| Maryland State Directory of New Hires- Monthly Invoice (see Section 2.24) | By the 15th of each month for services provided in the previous month | State Project Manager |  |
| Corrective Action Plan (CAP) (see Sections 3.4.2 (A)(7), 3.4.2 (A)(24) and 3.4.2 (B)(2). | Within five (5) business days or as requested or required by the State Project Manager. | State Project Manager |  |
| Database Adjustments (see Section 3.4.2 (A)(13)). | Thirty (30) calendar days after notice of Contract award, and within 30 calendar days of notification of changes in federal or State requirements until the Contract expires. | State Project Manager |  |
| Updated NHEIP (see Section 3.4.2 (A)(14) and 3.4.6 (F)(6)). | At Transition-In due within five (5) business days after the Contract start date and within ten (10) days after implementation of any new law, change or request from the State Project Manager. | State Project Manager |  |
| Maryland New Hire Monthly Reporting Statistics (Attachments U, U-1) (see Section 3.4.2 (A)(15)). | The first report is due 60 days after the Contract start date. Subsequent reports are to be submitted with the Maryland State Directory of New Hires- Monthly Invoice, for the previous reporting month | State Project Manager |  |
| Annual Report (Attachment V) (see Section 3.4.2 (A)(16)). | By the 1st of April each year - 10 hard copies and one CD | State Project Manager |  |
| Non-Compliant Employers Report (Attachment O) (see Section 3.4.2 (A)(18)(a)). | Quarterly from the date of the NTP. | State Project Manager |  |
| Employees Not Reported by Employer Report (Attachment O-1) (see Section 3.4.2 (A)(18)(b)). | Within five (5) business days of receipt of the quarterly Federal EPP report | State Project Manager |  |
| Problem Escalation Procedure (see Section 3.4.2 (C)(3)). | Within 10 days after the start of each Contract year (and within 10 days after any change in circumstance which changes the Procedure). | State Project Manager |  |
| Draft Disaster Recovery Plan (DRP) (see Section 3.4.3 (B)(12)). | Within 30 days after the Contract start date. | State Project Manager |  |
| Final Disaster Recovery Plan (DRP) (see Section 3.4.3 (B)(12)). | Within ninety (90) days after the receipt of the NTP | State Project Manager |  |
| Initial Project Schedule (see Section 3.4.5 (A)). | Within three (3) calendar days from the NTP, and updated on a weekly basis. | State Project Manager |  |
| Project Management Plan (see Section 3.4.5 (B)(1)). | Within seven (7) calendar days from receipt of the NTP. | State Project Manager |  |
| Communications Plan (see Section 3.4.5 (B)(2)) | Within seven (7) calendar days from receipt of the NTP. | State Project Manager |  |
| Cost Management Plan (see Section 3.4.5 (B)(3)) | Within seven (7) calendar days of receipt of the NTP | State Project Manager |  |
| Final Human Resource Management Plan (see Section 3.4.5 (B)(5)). | Within seven (7) days of receipt of the NTP. | State Project Manager |  |
| Weekly Status Report (see Section 3.4.5 (C)). | Monday of each week during the project implementation. | State Project Manager |  |
| Administrative and Operational Procedures Manual (see Section 3.4.6 (H)) | Draft Manual is due 15 calendar days after the contract start date. The final Manual is due within 15 days after approval of the draft. | State Project Manager |  |
| Transition-In Plan (see Section 3.4.6 (A), (B), (C), (D), and (E)) | Within fifteen (15) calendar days after Contract start date | State Project Manager |  |
| Transition-In Implementation Report (Attachment W) (see Section 3.4.6 (I)) | During the Transition-In Period, by noon Friday, on a weekly basis | State Project Manager |  |
| End of Contract Transition-Out Plan and final turnover plan (see Section 3.4.7 (B) and (H)) | Six (6) months prior to the end of the Contract | State Project Manager |  |
| Weekly Transition-Out Implementation Report (Attachment X) (see Section 3.4.7 (N)) | Weekly during the 60 Day Transition-Out period. | State Project Manager |  |
| Prime Contractor Unpaid MBE Invoice Report (Attachment J) and the Subcontractor Payment Invoice Report (Attachment K) (see Section 2.33) | By the 15th of the month following the report month. Copies of these forms are also to be submitted to the DHR MBE Liaison (address on forms). | State Project Manager |  |
| Current Certificates of Insurance (see Section 2.35) | At each Contract anniversary date including option periods, if exercised. Written notification of non-renewal and/or cancellation from the issuer of the insurance policies is due at least forty-five days before the expiration of said policies. In the event the State receives a notice of non-renewal and/or cancellation, an insurance policy from another carrier is due at least thirty days prior to the expiration of the non-renewed insurance policy. | State Project Manager |  |
| Quarterly Report of Economic Benefits Attained (see Section 4.2I) | By the 15th of the month following the end of the report quarter. The quarterly report shall be submitted until all proposed economic benefits are attained. | State Project Manager |  |
| Annual Outreach Plan (see Section 3.4.2 (A)(22)) | Initially within 30 calendar days of NTP, then on January 15th of each year of the Contract for the upcoming calendar year. | State Project Manager |  |

| MEETINGS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Meeting Requirement / Section | Frequency of Meeting | Location of Meeting | Length of Meeting | Date Meeting Held / Initials |
| Post-Award Conference (Section 3.7) | Once | TBD | TBD |  |

| CONTRACT CLOSE OUT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Submit to the State Project Manager the Transition-Out Plan | At six months before the end of the Contract’s base period | Submission of Plan | State Project Manager |  |
| Report any outstanding deliverables and/or tasks and time frames for completion. | At six months before the end of the Contract’s base period; On-going during the Transition-Out Period | Dated communications and/or report of outstanding deliverables and or/tasks and time frames for completion | State Project Manager |  |
| Provide a strategy for ensuring that all Contract documentation has been updated to reflect all changes, enhancements, modifications, etc., and has been delivered to DHR | At six months before the end of the Contract’s base period; On-going during the Transition-Out Period | Receipt of strategy | State Project Manager |  |
| Assure that all required support training, and transition information has been transitioned to the State Project Manager | During 60-Day Transition-Out Period | Receipt of support training and transition information and assurance from Contractor | State Project Manager |  |
| Assure that all electronic data files from the Contractor’s system have been made available on CD or other applicable medium and format (determined) at the time of turnover | During 60-Day Transition-Out Period | Receipt of electronic data files and assurance from Contractor | State Project Manager |  |
| Cooperate with facilitating the transfer of operations prior to the expiration of the Contract | During 60-Day Transition-Out Period | TBD | State Project Manager |  |
| Submit a final turnover plan | At six months before the end of the Contract’s base period; On-going during the Transition-Out Period | Submission of report | State Project Manager |  |
| Complete all turnover activities as provided for in the Contractor’s turnover plan and within DHR-approved timeframes that will enable the successful takeover of the operation with no delays or decreases in services. | On-going during the Transition-Out Period | TBD | State Project Manager |  |
| Cooperate with the incoming Contractor and provide requested documentation by the defined deadline, participate in meetings, completed assigned tasks in accordance with the incoming Contractors work plan, and behave in a courteous, and professional manner at all times in order to effectuate a seamless transition. | On-going during the Transition-Out Period | TBD | State Project Manager |  |
| Work during the Transition-Out period as if time is of the essence, because this period of time provides an opportunity for the new Contractor staff to gain a full understanding of the technical environment in order to provide all the services outlined in this RFP and thereby support all system users. | On-going during the Transition-Out Period | TBD | State Project Manager |  |
| Submit a revised system documentation report. | No less than thirty (30) calendar days before the end of the Contract during the Transition-Out phase | Submission of report | State Project Manager |  |
| Provide a three-month supply of forms and notices for the incoming vendor | During 60-Day Transition-Out Period | Submission of forms. | State Project Manager |  |