| START-UP ACTIVITIES – IDENTIFY AS DAILY, WEEKLY, MONTHLY, OTHER (as necessary) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Post-Award Orientation Conference | 30 days after Contract Award | Sign-In Sheets | State’s Contract Manager |  |
| State Personnel Agency Contact Information to be given to the Contractor | Prior to Commencement of Contract | Acknowledgement of Receipt | Contractor’s Project Manager |  |
| Contract Affidavit (Attachment C) | Within 5 days after recommended award | Signed and Dated Contract Affidavit | Procurement Officer |  |
| Hiring Agreement (Attachment H) | Within 10 days after recommended award | Signed and Dated Hiring Agreement | DHR Hiring Agreement Rep and one copy to the Procurement Officer |  |
| Certificates of Insurance | Within 10 days after recommended award | Copy of current Certificate of Insurance meeting all limit requirements | Procurement Officer |  |

| FULL PERFORMANCE ACTIVITIES – DAILY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Daily Scope of Work Activities as Listed in Section 4.3 | On Demand/As required by Services being provided | Signed and Dated Court Dockets | Contractor’s Project Manager |  |
| Case appointments assigned by the Maryland Circuit Court for each Maryland jurisdiction | As required per case | Signed and Dated Court Dockets | Contractor’s Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – WEEKLY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity |  | Time Frame |  | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Scope of Work Activities as Listed in Section 4.3 |  | On Demand/As required by Services being provided |  | Signed and Dated Court Dockets | Contractor’s Project Manager |  |
| Case Files and Statistics APS/APGRB Client Intake Form Attachment (O-1) |  | Shall be continuously updated within one (1) week after any activity |  | Signed and Dated Court Dockets | Contractor’s Project Manager |  |
| FULL PERFORMANCE ACTIVITIES – MONTHLY |  |  |  |  |  |  |
| Activity | Time Frame |  | Evidence of Completion |  | Evidence Received/Approved By | Date Received / Initials |
| APS/APGRB Training Verification Form (Attachment N-1) | Submitted thirty (30) days after the conclusion of each CINA/TPR training session. |  | Case file documentation |  | State Project Manager |  |
| Appeals: The Contractor shall discuss with the client, as developmentally appropriate, the possibility and ramifications of filing an appeal. (Section 4.4.E) | As required per case |  | Case file documentation |  | Contractor’s Project Manager |  |
| Continuity of Representation: The Contractor shall assign each client’s case to a specific attorney and take appropriate measures to ensure continuity of representation for all clients. (Section 4.4) | As required per case |  | Case file documentation |  | Contractor’s Project Manager |  |
| Report in writing via the Case Postponements and Conflict Report (Attachment L) any change in the client’s assignment, to the State’s Project Manager (Section 4.5) | (30) days after the change has been made by the Contractor. |  | Case file documentation |  | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – ANNUALLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Annual Continuing Legal Education and Training Certification Letter (Attachment N-2) | Due within thirty (30) days after the conclusion of each contract year. | Signed and Dated on Contractor’s Letterhead | State Project Manager |  |
| APS/APGRB Contractor Annual Monitoring Report (Attachment Q-1) | Due within thirty (30) days after the conclusion of each contract year. | Signed and Dated | Program Manager |  |
| On-Site Annual Monitoring Contractor shall ensure that client case files and are available for an on-site annual monitoring visit by the State Project Manager or designee | To be determined by MLSP | Signed and Dated Documentation | State Project Manager |  |
| On-Site Annual Monitoring Contractor shall ensure that client case files and are available for an on-site annual monitoring visit by the State Project Manager or designee | To be determined by MLSP | Signed and Dated Documentation | State Project Manager |  |

| REPORTS |  |  |  |
| --- | --- | --- | --- |
| Report Requirements / Section | Time Frame | Report Sent To | Date Received / Initials |
| APS/APGRB Hearings Request for Payment Summary (Attachment (I-1) | Due by the 15th of each month for the preceding month’s activities | State Project Manager |  |
| Case Postponement and Conflicts Report (Attachment L) | Due by the 15th of each month for the preceding month’s activities | State Project Manager |  |
| APS/APGRB Training Verification Form (Attachment N-1) | Due within (30) days at the conclusion of each APS/APGRB-related training | State Project Manager |  |
| Annual Continuing Legal Education and Training Certification Letter (Attachment N-2) | Due within thirty (30) days after the conclusion of each contract year including the option years if exercised | State Project Manager |  |
|  | REPORTS |  |  |
| APS/APGRB Contractor Annual Monitoring Report (Attachment Q-1) | Due within thirty (30) days after the conclusion of each Contract year | State Project Manager |  |
| Quarterly Report of Economic Benefit Attained (see Section 6.2 J) | Due by the 15th of the month following the end of the report quarter | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – OTHER (one time only, as requested, etc.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| General Contract Monitoring: Contractor shall cooperate with MLSP in the performance of the Contract Monitoring sessions. (Section 5) | As required | Signed and Dated Documentation | State Project Manager |  |
| Contractor shall cooperate with the State for announced or unannounced Contract monitoring visits as deemed appropriate by the State. (Section 5) | As required | Signed and Dated Documentation | State Project Manager |  |
| Compliance Audits Contractor shall cooperate with the State for routine, periodic or special compliance audits deemed appropriate by the State. | As required | Signed and Dated Documentation | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – OTHER (one time only, as requested, etc.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Transition of Case Files: If the State Project Manager or the court determines it is in the best interest to do so the Contractor shall remain the attorney of record, at the expiration of any Contract, for all proceedings and Appeals for the duration of the Court's jurisdiction over the client. All case files and documentation generated by the Contractor or MLSP during the term of the Contract or the attorney's representation of a client shall be retained by the Contractor for a period of three (3) years following the termination or expiration of the Contract, expiration of the attorney's representation, or the conclusion of any audit. | Three (3) years following the expiration of the Contract. | Receipt of requested documentation | State Project Manager |  |

| Transfer of Cases the Contractor shall fully cooperated with the transfer of any client case. Cooperation shall include, but is not limited to delivering and/or receiving all case files in a period. | Not to exceed thirty (30) days after receiving a written request from the State Project Manager. | Receipt of requested documentation | State Project Manager |  |
| --- | --- | --- | --- | --- |

| MEETINGS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Meeting Requirement / Section | Frequency of Meeting | Location of Meeting | Length of Meeting | Date Meeting Held / Initials |
| One-On-One Follow-Up Meeting | Three (3) months after the Contract start date | Client’s Placement Location or Courthouse if the case circumstances dictate that this setting is best for the client | As required |  |
| Attorney in Person Contract With the client in the client's placement location with and investigator, case worker license social worker | Once every six (6) months | Client’s Placement Location or Courthouse if the case circumstances dictate that this setting is best for the client | As required |  |

| CONTRACT CLOSE OUT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| After the close of each Contract year, including at the close of each option year (if exercised) the final invoice shall be submitted within thirty (30) days in order to be considered for payment. Invoices submitted after this time will not be considered for payment. Final payment will not be made until after receipt of the Annual Report. | At the end of the contract term | Sign and Dated Documentation | State Project Manager |  |