AGENCY CONTROL #: CSEA/GUIDE/13-001-S

ATTACHMENT: Attachment G

SOLICITATION TITLE: Maryland Child Support Guidelines

| START-UP ACTIVITIES – IDENTIFY AS DAILY, WEEKLY, MONTHLY, OTHER (as necessary) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Submission of Contract Affidavit to the Procurement Officer | Within 10 work days of notification of award | Submission of Contract Affidavit | Procurement Officer |  |
| Provide Problem Escalation Procedure (Section 3.4.I) | Due at the Post Award Orientation Conference and within 10 days after any change in circumstance which changes the Procedure | Submission of Procedures | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – DAILY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |

| FULL PERFORMANCE ACTIVITIES – WEEKLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |

| FULL PERFORMANCE ACTIVITIES – MONTHLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |

| FULL PERFORMANCE ACTIVITIES – ANNUALLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |

| FULL PERFORMANCE ACTIVITIES – OTHER (one time only, as requested, etc.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Review the Guidelines Schedule and compare Maryland’s Guidelines against those of Maryland’s border-States using the Income Shares Model. | October 8, 2012 | Report (See Section 3.4.C) | State Project Manager |  |
| Provide testimony to the House and Senate Committees in the event that a bill is filed in the Maryland General Assembly to revise the Guidelines. Testimony will include, but is not necessarily limited to, responding to questions verbally and/or in writing from the Committees. | Testimony may be required at any time during the 90-day session, which begins January 2013 and ends April 2013. |  | State Project Manager |  |
| Provide technical assistance including, but not limited to, responding to inquiries and any residual issues of the General Assembly, as well as questions pertaining to the Guidelines Review and Schedule. | Entire Contract term |  | State Project Manager |  |

| REPORTS |  |  |  |
| --- | --- | --- | --- |
| Report Requirements / Section | Time Frame | Report Sent To | Date Received / Initials |
| Develop and submit a State Guidelines Comparison Report (Section 3.4.C) | October 8, 2012. | State Project Manager |  |
| First draft of the updated Guidelines Schedule and Alternative Schedule for High and Low Income Levels (Section 3.4.D) | October 8, 2012 | State Project Manager |  |
| Second draft of the updated Guidelines Schedule and Alternative Schedule for High and Low Income Levels (Section 3.4.E) | November 8, 2012 | State Project Manager |  |
| Ten (10) bound reports and one (1) camera- ready report of the final Guidelines Schedule and Alternative Schedule for High and Low Income Levels (Section 3.4.F) | December 1, 2012 | State Project Manager |  |

| MEETINGS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Meeting Requirement / Section | Frequency of Meeting | Location of Meeting | Length of Meeting | Date Meeting Held / Initials |
| Post Award Orientation Conference (Section 3.7) | Once | TBD | TBD |  |
| Contractor’s Project Manager shall be available to discuss Contract progress, as well as participate in any teleconferences pertaining to the same (Section 3.6). |  |  |  |  |

| CONTRACT CLOSE OUT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |