AGENCY CONTROL #: SSA/RCP/14-001-S

ATTACHMENT: Attachment F

SOLICITATION TITLE: Respite Care Services

| START-UP ACTIVITIES – IDENTIFY AS DAILY, WEEKLY, MONTHLY, OTHER (as necessary) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Start-Up Scope of Work Activities as Listed in Sections 3.3 and Grantee Requirements in Section 3.4 (B) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Submit Electronic Funds Transfer Form (Attachment D) to the Comptroller’s Office. See Section 2.20 | Upon notification of selection for award | Submission of form. | State Comptroller’s Office |  |
| Certificates of insurance. See Section 2.26. | Within ten (10) working days after recommendation of award. | Current Certificate of Insurance meeting all limit requirements | Procurement Officer |  |
| Collaborate with each LDSS in the regions proposed in order to promote referrals and encourage service utilization between both agencies. Grantees shall submit a completed Grantee/Department of Social Services Agreement (Attachment H) verifying contact with LDSS in the regions. See Section 3.4 (B)(3) | No later than thirty (30) days after notification of Grant award | Submission of completed Agreement | State Project Manager |  |
| Provide a Problem Escalation Procedure. See Section 3.6 (B). | No less than 10 business days prior to the beginning of the grant | Submission of Problem Escalation Procedure | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – DAILY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Daily Scope of Work Activities Listed in Sections 3.3 and Grantee Requirements in Section 3.4 (B) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Provide respite care services to all eligible clients who have either Functional or Developmental disabilities and reside in one of the regions designated in Section 3.3 D. Services shall be provided to clients needing either Level I or II care using one or more of the delivery models described in Section 3.3 A. See Section 3.4 (B) (1) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Provide an application for service to the client/family. See Section 3.4 (B)(1)(a) | Within 3 business days after receipt of a request from the client/family | Dated communications between Grantee and State | State Project Manager |  |
| Determine client eligibility. See Section 3.4 (B)(1)(b) | Within thirty (30) calendar days after receipt of a completed application | Determination of client eligibility | State Project Manager |  |
| Develop and implement a service plan. See Section 3.4 (B)(1)(c). | On Demand/As required by Services being provided | Service Plan | State Project Manager |  |
| Re-determine eligibility and reconsider the service statement if a change occurs which affects eligibility or the need for service. If there is no change, re-determine and reconsider at least every 12 months. See Section 3.4 (B)(1)(d) | On Demand/As required by Services being provided | Dated communications between Grantee and State | State Project Manager |  |
| Terminate services as described in COMAR 07.02.18.09 (Attachment I) See Section 3.4 (B)(1)(e) | On Demand/As required by Services being provided | Dated communications between Grantee and State |  |  |
| Provide sufficient qualified staff to deliver respite care services in accordance with COMAR 07.02.18.11 (Attachment I). Any care workers employed by the Grantee shall be (at minimum) Certified Nursing Assistants (CNAs), as required by the Maryland Board of Nursing, if they are to perform personal care tasks for clients receiving Level I care. See Section 3.4 (B)(2) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Develop and implement outreach activities designed to ensure that agencies, organizations and individuals in the community/geographic regions proposed know about respite care services and how to access them. See Section 3.4 (B)(3) | On Demand/As required by Services being provided | Outreach activities. Dated communications between Grantee and State | State Project Manager |  |
| Establish and maintain a case record on each eligible client in accordance with COMAR 07.02.18.06 (Attachment I). See Section 3.4 (B)(5) | On Demand/As required by Services being provided | Case records | State Project Manager |  |
| Maintain client contact information (name, address, telephone number, and e-mail address, if available) which may be utilized by DHR/OAS for the purpose of conducting an independent client satisfaction survey. Section 3.4 (B)(6) | On Demand/As required by Services being provided | List of client contact information | State Project Manager |  |
| Maintain a Problem Escalation Procedure for both routine and emergency situations. See Section 3.6 (A) | On Demand/As required by Services being provided | Submission of report/resolution of issue | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – WEEKLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Weekly Scope of Work Activities Listed in Sections 3.3 and Grantee Requirements in Section 3.4 (B) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Submit to client contact information to DHR/OAS via email upon request. See Section 3.4 (B)(6). | Within 2 weeks after request | Receipt of client information | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – MONTHLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Monthly Scope of Work Activities Listed in Sections 3.3 and Grantee Requirements in Section 3.4 (B) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Submit monthly invoice (Attachment A-1) See Section 2.19. | By the 15th calendar day of each month | Receipt of invoice | State Project Manager |  |
| Submit Monthly Client Service Report (Attachment G) This report is to be submitted with the monthly invoice. See Section 2.19 and Section 3.4 (B)(7) | By the 15th calendar day of each month | Receipt of Report | State Project Manager |  |
| Make accounts and records available to representatives of DHR/OAS and other DHR staff authorized to inspect such records. See Section 3.4 (B)(8) | Upon written request | Receipt of accounts and records | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – ANNUALLY |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Annual Scope of Work Activities Listed in Sections 3.3 and Grantee Requirements in Section 3.4 (B) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Certificates of insurance. See Section 2.26 | at each Grant anniversary date during the Grant period, or as directed by the State | Current Certificate of Insurance meeting all limit requirements | State Project Manager |  |
| Provide a Problem Escalation Procedure. (See Section 3.6 (B) | Within 10 days after the start of each Grant year | Submission of Problem Escalation Procedure | State Project Manager |  |

| FULL PERFORMANCE ACTIVITIES – OTHER (one time only, as requested, etc.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| “Other” Scope of Work Activities Listed in Sections 3.3 and Grantee Requirements in Section 3.4 (B) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Comply with all processes and requests made by the State Project Manager in conducting monitoring oversight activities during the term of the Grant. See Section 3.5 (A) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Allow State Project Manager to complete scheduled and unscheduled site visits to assess performance, Grant Compliance, and report on delivery of services required under this Grant. See Section 3.5 (B). | As appropriate/On Demand/As required by the Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Provide a Problem Escalation Procedure (See Section 3.6 (B) | Within 10 business days after any change in circumstance which changes the Procedures | Submission of Problem Escalation Procedure | State Project Manager |  |

| REPORTS |  |  |  |
| --- | --- | --- | --- |
| Report Requirements / Section | Time Frame | Report Sent To | Date Received / Initials |
| Monthly Invoice (Attachment A-1). See Section 3.7 (A) | By the 15th of each month following the month services were provided. | State Project Manager |  |
| Client Services Report (Attachment G). See Section 3.7 (B) | Electronically by the 15th of each month following the month services were provided | State Project Manager |  |
| List of client contact information. See Section 3.7 (C). | To be e-mailed within two weeks after request from OAS. | State Project Manager |  |
| Current Certificates of Insurance. See Section 3.7 (D). | Due at each Grant anniversary date including option periods, if exercised. | State Project Manager |  |

| MEETINGS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Meeting Requirement / Section | Frequency of Meeting | Location of Meeting | Length of Meeting | Date Meeting Held / Initials |
| Post-Award Orientation Conference. See Section 3.9 | Within two weeks prior to the Grant start date | TBD | TBD |  |
| Exit conference. See Section 3.4 (B)(9). | Within thirty (30) calendar days prior to Grant termination | TBD | TBD |  |

| GRANT CLOSE OUT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Time Frame | Evidence of Completion | Evidence Received/Approved By | Date Received / Initials |
| Grant Close Out Scope of Work Activities Listed in Sections 3.3 and Grantee Requirements in Section 3.4 (B) | On Demand/As required by Services being provided | Unscheduled site visits from State Project Manager | State Project Manager |  |
| Participate in an exit conference with to review and discuss the return of current client information to DHR/OAS. (See Section 3.4 (B)(9) Note: The State Project Manager will negotiate a due date with the Grantee for the return of client information on an individual basis. | Within thirty (30) calendar days prior to Grant termination | Attendance sheet from exit conference | State Project Manager |  |